## P1 - TaskTracker
Task Type | Task Name | Phase | Status | Start Date | Expected End Date | Actual End Date | Description | Useful Links
Project Setup | Create Maven Project | P1 | Completed |  |  |  | Parent-POM created Child POM created
| Checkin Project In GitHub | P1 | Completed |  |  |  | Completed using the ‘GitHub Desktop’ software | 1) http://stackoverflow.com/questions/17552457/how-do-i-upload-eclipse-projects-to-github 2) https://help.github.com/articles/connecting-to-github-with-ssh/
| Create following for Database Setup: - DB Instance and Tables - Create Triggers for History Data - Insert Master Data | P1 | Completed |  |  |  | Database and Tables creation scripts for basic following modules are ready: - OFDS
| Project Setup Documentation | P1 |  |  |  |  | Set up project from scratch on a new machine:: Include all below steps: 1. Required Software Installation (Open-JDK, GIT, Maven, DB[MySQL]) 2. Git Checkout, Maven Build, Deployment 3. DB setup 4. Welcome Page | Google Drive Folder: \MyWork\SuperMarket\project-documents
| Health Check | P1 |  |  |  |  | Actuator URL showing the health status of different aspects/modules in application: 1. Database Status 2. Email/SMTP Server Status 3. | status is DOWN
| PostMan Workspace for Test Automation | P1 | [5 empty] | http://blog.getpostman.com/2017/07/28/api-testing-tips-from-a-postman-professional/ https://learning.getpostman.com/docs/postman/scripts/intro_to_scripts https://learning.getpostman.com/docs/postman/scripts/test_examples https://learning.getpostman.com/docs/postman/scripts/test_scripts https://www.youtube.com/watch?v=Qlvbc6kIBOk https://www.youtube.com/watch?v=juldrxDrSH0&list=PLhW3qG5bs-L-oT0GenwPLcJAPD_SiFK3C
| QA - Sonar Project Setup | P4 |  |  |  |  | No Critical, Major (<25), JavaDocs, Code Formatting, Code Coverage
| CI - Jenkins Setup | P4
Requirements | Prepare a list of User Stories in 1-2-3 iterations - [P2 - UseCases] | P1 |  |  |  |  | Created module wise "Functional Requirement" sheet in each module. List all tasks in each iterations Work on 1st iteration First Prepare list of UI, Fields, field type, label names etc
REST / Spring Framework | Spring REST Service produces JSON | P1 |  |  |  |  | Spring MVC done REST producing JSON done | http://stick2code.blogspot.com/2014/03/solved-orgspringframeworkwebhttpmediaty.html
| Spring MVC w/o xml, with Annotation | P1 |  |  |  |  | Converted into web.xml less config. Using two Dispatcher Servlet, 1) for Rest API (/api/*) and other for all other purpose (/) | http://www.baeldung.com/spring-xml-vs-java-config http://www.robinhowlett.com/blog/2013/02/13/spring-app-migration-from-xml-to-java-based-config/ http://java-journal.blogspot.in/2012/08/what-is-applicationcontext-what-are-its.html https://stackoverflow.com/questions/28877982/spring-java-config-with-multiple-dispatchers
| REST Resources Identify | P1 |  |  |  |  | ProductCategory Resource Identified Others Resource identification in progress
| REST HTTP Methods identified | P1 |  |  |  |  | GET, POST, PUT, DELTE identified and implemeneted with Success and Error schenarios
| Using HTTP Headers - ContentType=application/json | P1 |  |  |  |  | Please read the implementation doc: \MyWork\SuperMarket\project-documents\rest-tute\RESTWebService_HTTP-Headers.docx
| REST URL Design | P1 |  |  |  |  | Also check cookbook | https://dzone.com/articles/7-rules-for-rest-api-uri-design-1
| Using HTTP Status Code | P1 |  |  |  |  | Implemented using RestResponseBodyAdvice 1) responseBean.setStatusCode(servletResponse.getStatus()); 2) servletResponse.setStatus(((ResponseBean<Object>) body).getStatusCode()); | http://www.restapitutorial.com/httpstatuscodes.html http://blog.restcase.com/top-5-rest-api-security-guidelines/
| REST Service Error Handling | P1 |  |  |  |  | Implemented using @ControllerAdvice, RestResponseEntityExceptionHandler and ErrorBean This also handle any validation error found in [@Valid @RequestBody] in controller method, if BindingResult is not passed in method argument. In case BindingResult is passed, then this validation exception is not thrown and handled in RestResponseEntityExceptionHandler. | http://www.baeldung.com/global-error-handler-in-a-spring-rest-api
| REST Service Success response structure | P1 |  |  |  |  | { "responseTime": 0, "statusCode": 200, "successMessage": "OK", "data": [] } SUCCESS { "errorList": [ "firstName: first name length should be between 5 and 50 characters" ], "errorCode": "VALIDATION_ERROR", "errorMessage": "The request from client has some validation error in input data" } ERROR - Update Doc with example of Request/Response data for both success/error scenario with both json/xml formats. - In case of validation error, the response format is not proper | 1. http://www.baeldung.com/global-error-handler-in-a-spring-rest-api 2.
| JSON to Date and vice versa conversion | P1 |  |  |  |  | Implemented using @JsonFormat annotation
| Versioning the REST API | P1 |  |  |  |  | Implemented using the use case @ https://github.com/mindhaq/restapi-versioning-spring. Using Accept/ContentType headers for version - More Read: http://www.baeldung.com/rest-versioning - Accepted Solution: prepend /v2/ in resource uri -------------------------------------------------------------- - Also check Discovery Tool for the @Api annotations - Also understand the meaning of Content Negotiation in REST. - http://www.baeldung.com/spring-mvc-content-negotiation-json-xml | http://stackoverflow.com/questions/20198275/how-to-manage-rest-api-versioning-with-spring
| Internationalization (i18n) and localization (l10n) | P1 |  |  |  |  | Following from locale specific files: 1. Error Message (Completed) 2. General Labels & messages (Completed) Hint from Discovery | http://www.mkyong.com/spring-mvc/spring-mvc-internationalization-example/ http://howtodoinjava.com/spring/spring-mvc/spring-mvc-internationalization-i18n-and-localization-i10n-example/ https://stackoverflow.com/questions/28633390/validation-message-not-found http://docs.oracle.com/javaee/6/tutorial/doc/gkahi.html
| Input Validation | P1 |  |  |  |  | More Read: http://blog.restcase.com/top-5-rest-api-security-guidelines section 2/5 - Input Validation javax.validation is specification from Oracle/Java hibernate-validator is one of the Implementation of above spec (see image) | https://stackoverflow.com/questions/8756768/annotations-from-javax-validation-constraints-not-working http://www.baeldung.com/javax-validation https://docs.jboss.org/hibernate/validator/4.1/reference/en-US/html/validator-usingvalidator.html#validator-usingvalidator
| Input Validation - On Dynamic Field | P2 |  |  |  |  | Apply dynamic validation of specific field. For example apply 8 digit Integer type validation on UserName field which is of String Type. Design a framework for this dynamic validation.
| REST API YML Documentation | P1 | [5 empty] | http://www.baeldung.com/swagger-2-documentation-for-spring-rest-api https://howtodoinjava.com/swagger2/swagger-spring-mvc-rest-example/ https://github.com/springfox/springfox/issues/1499
| Pagination | P1 | Completed |  |  |  | RESTful+Best+Practices.pdf for reference | https://s3.amazonaws.com/tfpearsonecollege/bestpractices/RESTful+Best+Practices.pdf
| Sorting | P1 | Completed |  |  |  | RESTful+Best+Practices.pdf for reference
| Searching | P1 |  |  |  |  | RESTful+Best+Practices.pdf for reference
| Date/Time Handling | P1 |  |  |  |  | RESTful+Best+Practices.pdf for reference
| REST Caching | P1 |  |  |  |  | RESTful+Best+Practices.pdf for reference | https://www.infosys.com/digital/insights/Documents/restful-web-services.pdf
Unit Testing | JUnit 5 Testing Framework | P1 | Completed |  |  |  | http://www.softwaretestingclass.com/what-is-difference-between-unit-testing-and-integration-testing/ Test Driven Developement:: https://www.youtube.com/watch?v=Xc3d6j8Rm_I https://www.youtube.com/watch?v=T38L7A0xP-c | http://www.baeldung.com/junit-5-preview http://www.baeldung.com/junit-vs-testng http://www.baeldung.com/junit-5
| JUnit Testing Framework | P1 | Completed |  |  |  | WebConfig.java WACTestConfiguration.java StandaloneTestConfiguration.java | https://www.petrikainulainen.net/programming/spring-framework/unit-testing-of-spring-mvc-controllers-configuration/
| Testing Spring REST Controllers | P1 | Completed |  |  |  | Test controllers using mockMvc, as it is also used in current project. Implemented in ALLControllerTest, testing of: 1) Status Code 2) Media Type 3) JSON/XML Payload | https://www.petrikainulainen.net/programming/spring-framework/unit-testing-of-spring-mvc-controllers-normal-controllers/ http://www.baeldung.com/spring-webappconfiguration http://www.baeldung.com/integration-testing-a-rest-api
| Parallel Execution of Junit | P1 |  |  |  |  | Hint from alt ria
| Using Spring Profile for separate test app context | P1 | Completed |  |  |  | 2 profiles (test & production) used. prod configured in web.xml, while test configured in Test-Configurations using @ActiveProfiles("test") | Refer debapriya's email/pdf file: [Test cases with DB integration.pdf]
| Testing with In-Memory/MySQL Database using different data-source | P1 | Completed |  |  |  | Use of In-Memory db for test cases; also refer howtodoinjava separate test-db should be created/initialized during running test. refer discovery-tool for that implementation | [BEST] https://www.mkyong.com/spring/spring-embedded-database-examples/ 1. http://ahexamples.blogspot.in/2014/05/example-of-junit-hsqldb-sproc-call.html 2. http://howtodoinjava.com/best-practices/how-you-should-unit-test-dao-layer/ 3. http://simpletoad.blogspot.in/2012/10/h2-vs-hsqldb.html
Automation Testing | Selenium Automation Tool with CATS Framework
Performance Testing | JMeter Setup | P4 |  |  |  |  | Check PM (CPU, No of Threads), no of requests pass/fail etc | https://stackoverflow.com/questions/20143401/how-to-analyze-a-jmeter-summary-report
| Log Analysis Tool - Splunk | P4 |  |  |  |  | Check the different category of logs based on - Users (userId/userName), Exceptions (RuntimeException, ParseException etc. zero NullPointerException), external integration failure (increase connection timeout), LogLevel (debug, info, error etc) Print enough information in Error Logs so that it could be debug in production
| Burp Suit Testing | P4
JDBC / Tx Mgmt | JPA/Hibernate - Integration with Spring | P1 | Completed
| JPA/Hibernate - Tx with AOP / Annotation | P1 | [5 empty] | https://www.java-success.com/spring-javaconfig-configuration-and-transactionmanager/
| JPA/Hibernate - Annotation Mapping General | P1 | Completed
| JPA/Hibernate - Annotation Mapping User Group | P1 | Completed
| JPA/Hibernate - Annotation Mapping Address | P1 |  |  |  |  | Learn Inheritance in JPA for this. Especially an example of Person having two addresses (billingAddress and deliveryAddress) | https://en.wikibooks.org/wiki/Java_Persistence/Inheritance https://www.thoughts-on-java.org/complete-guide-inheritance-strategies-jpa-hibernate/
| JPA/Hibernate - Annotation Mapping Created/Updated By | P1
| JPA/Hibernate - Annotation Mapping History | P1
| JPA/Hibernate - Performance | P1 | [5 empty] | https://www.thoughts-on-java.org/hibernate-logging-guide/
| JPA/Hibernate - Spring Data JPA | P1
Loading of Properties | Environment Specific Properties/YAML files for: - dev - test - prod | P1 | Completed |  |  |  | Using application-{envName}.yml files and setting -Dspring.profiles.active="{envName}" as jvm arguments. | https://www.baeldung.com/spring-yaml https://www.concretepage.com/spring-boot/spring-boot-profiles-example
| Uses Specific Properties/YAML File for - DB - Email - Encryption etc | P1 | Completed |  |  | https://www.callicoder.com/spring-boot-configuration-properties-example/ https://www.youtube.com/watch?v=0G9X-pTv_UU https://www.concretepage.com/spring-boot/spring-boot-profiles-example | Using spring.profiles.include property in our property file | https://www.callicoder.com/spring-boot-configuration-properties-example/ https://www.youtube.com/watch?v=0G9X-pTv_UU
| Updating of properties using - common-config jar - Spring Boot support (Do POC) | P1 | Completed |  |  |  | Some REST API that update the given properties specific a config type (message/dashboard, message/errors, jdbc, email etc) | https://www.javacodegeeks.com/2014/09/using-configurationproperties-in-spring-boot.html
Caching Data | JPA/Hibernate - Caching | P1 |  |  |  |  | Other cache implementation with Hibernate: http://howtodoinjava.com/hibernate/hibernate-oscache-configuration-example-tutorial/ | http://howtodoinjava.com/hibernate/understanding-hibernate-first-level-cache-with-example/ http://howtodoinjava.com/hibernate/how-hibernate-second-level-cache-works/ [BEST] http://www.baeldung.com/hibernate-second-level-cache
| Application Service Caching - ehCache | P1 |  |  |  |  | Check etme for eh-cache | http://www.baeldung.com/ehcache http://www.baeldung.com/spring-cache-tutorial https://howtodoinjava.com/spring-boot2/spring-boot-cache-example/
| ehCache - web management | P4
| Master Data caching using distributed cache | P5 |  |  |  |  | Redis implementation for example
UI / FrontEnd Framework | AngularJS - REST API using JSON | P1 | Completed
| AngularJS - Form Validation | P1 | Completed |  |  |  |  | http://www.baeldung.com/validation-angularjs-spring-mvc
| AngularJS - Login Page | P1 | Completed
| AngularJS - Table showing data | P1 | Completed |  |  |  | Table showing data with - Sorting option - Pagination - Filter on predefined columns (IsValid) - Page Size Dropdown - | http://plnkr.co/edit/xmjmIId0c9Glh5QH97xz?p=preview (Pagination) https://docs.angularjs.org/api/ng/filter/orderBy (Sorting) https://embed.plnkr.co/plunk/iP2NcF (pageSize dropdown)
| Multi Language Support - Switch Language | P1 | Completed |  |  |  | User can switch to language of its choice by selecting dropdown
| Multi Language Support - Multi Lang Labels | P1 | Completed |  |  |  | Example: https://ttdsevaonline.com/index.html#/welcome
Security | Authentication - Framework - Local DB | P1 | Completed |  |  |  | Login using username(or email or mobile) and hash(password) in local db. OAuth 2 is not required here. Basic authentication with TLS (HTTPS) is best fit here.
| Password in db to be hashed | P1 | Completed |  |  |  | Hash of password to be stored in db, so that no one can see it or decode/decrypt it.
| Authentication - Framework - Social Login | P3 |  |  |  |  | Login using social authentication of Google/Facebook using OAuth 2.0
| Authorization - Framework? | P1 |  |  |  |  | Group, Role, User etc. User in a group can access all resources/roles of its group. Also check authentication/authorization in the filter
| REST Service cookie/session management | P1 | Completed |  |  |  | All cookies should be HttpOnly and HTTPS
| User Profile Cookie to be Encrypted | P1 | Completed |  |  |  | To protect the UII and PII, encrypt the user cookie and decrypt it for every request.
| Authorization - REST Service Security - Group/Function based access to REST Services | P1 |  |  |  |  | User can access only those resources, which belongs to its group. Super Admin can access all the resources. | http://blog.restcase.com/top-5-rest-api-security-guidelines/
| Allow access to UnProtected URLs | P1 | Completed |  |  |  | Allow access to un secured URLs like /auth/login, /auth/reset-password
| Security - Spring Angular Integration | P2
Reports | Report - PDF Generate | P3
| Report - Excel Generate | P3
| Report - Print the report displayed on web | P3
Members DashBoard | Upcoming / Completed Events | P3
Registration, Login, Password Reset | User Registration | P2 |  |  |  |  | User Registration - Form Submit - Click Link to activate account
| Send EMail | P1
| Send SMS | P4
Application Logging | Generate Daily Logs | P1 |  |  |  |  | check "logback.xml" in source code Generate Daily Logs Archive Previous Day Log Logs outside war file | https://www.javacodegeeks.com/2011/01/10-tips-proper-application-logging.html?utm_content=buffer1aa47&utm_medium=social&utm_source=twitter.com&utm_campaign=buffer
| Each log contains logged in user name | P1 |  |  |  |  | Ref: ETME SLF4J & Discovery apps implemented using logback.xml and TracerFilter.java | https://logback.qos.ch/manual/mdc.html
| AOP Logging | P1 |  |  |  |  | Use AOP to INFO log the entry/exit/return-value statements
| Implement Logging Tips & Levels | P1 |  |  |  |  | Implement log levels like CONTROLLER, SERVICE, REPOSITORY etc to print log statements. Also update the doc with what should be the predefined log levels: LoggingAspect ->INFO CaughtException->ERROR https://www.javacodegeeks.com/2011/01/10-tips-proper-application-logging.html?utm_content=buffer1aa47&utm_medium=social&utm_source=twitter.com&utm_campaign=buffer | https://www.javacodegeeks.com/2014/07/how-to-instantly-improve-your-java-logging-with-7-logback-tweaks.html
JVM / Memory Leaks | Find Memory Leaks in App using JVisual VM | P2 | [5 empty] | https://dzone.com/articles/how-to-find-and-fix-memory-leaks-in-your-java-appl https://www.toptal.com/java/hunting-memory-leaks-in-java
Event Auditing | Log events for audit | P2
Event wise audit report
User wise audit report
History of all data/updates in db | Keep history of all db transactions | P1
Milestone First Phase | Framework Ready with All TECHNOLOGY | P1 |  |  |  |  | REST Tutorials & Blogs | http://blog.restcase.com/ http://www.baeldung.com/rest-with-spring-series/ https://www.narwhl.com/
Milestone Second Phase | Identify and Implement Primary Use Cases | P2
Milestone Third Phase | Identify and Implement Secondary Use Cases | P3
Milestone Forth Phase | Application Ready with All TOOLS | P4

## Architecture
maven application of pom type
has 4 modules
| 1. shop-web | web application of war type to be deployed in tomcat, dependent on shop-services
| 2. shop-services | collection of all business services. there could be multiple modules/services like dashboard, catalog management, checkout, reporting etc
| 3. shop-common | common classes across all controllers and modules or services like exception, entities etc
| 4. OpenFramework | its like collection of utils, tools which can be used in any jars, web apps etc
Also write the rules here that will be used in the application while development/coding.
| 1 | No entity should be used in web / controller layer
| 2 | All entity independent Utils should be in open framework and all dependent utils should be in shop-common module
| 3 | Keep all config / properties file either in service layer or common layer
| 4 | use of adapter should be to convert entity to vo and vice verca
| 5 | some more concrete rules
6
7
8

## P1 - TechnologyList
Technology Type | Technology Name | Version | Description
Language | Java / JDK | Open JDK 11
IDE | Eclipse / STS | Latest
| Eclipse Plugins | YEdit
| Sublime Text 2 | Sublime Text 2 | for node js dev
Distributed Revision Control System | Git / GitHub
UML Modeling Tool | BoUml | 4.2.1 is free in ubuntu | http://www.bouml.fr/download.html http://www.ibm.com/developerworks/rational/library/content/RationalEdge/sep04/bell/ | Astah-suggested by Partha | UML Designer (Eclipse Luna version) 5.0
Build Tool | Maven | Maven 3.4
Application Server | Tomcat 9.0/ Jboss / Jetty |  | debug in JBoss: http://stackoverflow.com/questions/516196/jboss-debugging-in-eclipse?answertab=votes#tab-top
Application Framework | MVC Framework | Spring MVC 5.x
| REST API | Spring REST
Persistence Framework | Hibernate | Hibernate 5.x
| Spring Data | Spring Data JPA
Cache | DB Cache | EHCache
| Distributed Cache | Hazelcast |  | Others are: Redis, ehCache
Database | MySQL | MySQL 5.7
Code Quality | Sonar | Sonar 5.1.1
FindBug Eclipse
Continuous Integration | Jenkins
Scheduling Framework | Spring Scheduler / Timer
File Searching | Everything | windows | Search files in file system during development
git bash: grep -r "search string" .
Java Decompiler | JD GUI
Performance Testing Tool | JMeter | latest
Log Analysis Tool | Splunk
Memory Analysis Tool | Eclipse Memory Analyser
Wily
At Technologies
Eclipse-MAT | JVM Memory | Not Used, Not Read
Wily - Licenced | JVM Memory | -NA-
Adviced Logging | Code Quality
JMeter - 4 PT | Code Quality |  | https://learn-jmeter.blogspot.in/ http://jmeter.apache.org/usermanual/generating-dashboard.html https://svn.apache.org/repos/asf/jmeter/tags/v3_0_RC2/docs/usermanual/generating-dashboard.html http://jmeter.apache.org/usermanual/best-practices.html
ESAPI | Security | Sanitize all user input data into application, check the implementation in ALT OWASP Top 10 - 2013 | https://www.owasp.org/index.php/Category:OWASP_Top_Ten_Project#tab=OWASP_Top_10_for_2013 http://www.baeldung.com/jvm-log-forging
CSRF | Security |  | https://insidethecpu.com/2013/09/23/encrypted-token-pattern/ https://adriancitu.com/2017/01/16/a-java-implementation-of-csrf-mitigation-using-double-submit-cookie-pattern/ https://www.owasp.org/index.php/Cross-Site_Request_Forgery_(CSRF)_Prevention_Cheat_Sheet#Encrypted_Token_Pattern https://dzone.com/articles/java-csrf-mitigation-double-submit-cookie-pattern
MS Visio | Design
YML instead of Properties | No Idea
Splunk 4 LogAnalysis | Code Quality
JConsole | JVM Memory
JVisualVM | JVM Memory
JMX | No Idea
Jenkins CI | CI
Sonar | Code Quality
XssSanitizerUtil | Security
ThreadContext | No Idea
Akamai
shared.loader | classpath | Making an extrenal directory behave as a classpath folder for all web-apps under the tomcat | http://flylib.com/books/en/4.15.1.24/1/
Sticky Session / Tomcat Cluster | Architecture |  | http://www.ramkitech.com/2012/11/tomcat-clustering-series-part-3-session.html http://www.ramkitech.com/2012/03/virtual-host-apache-httpd-server-tomcat.html
Burp Suite | Find errors in loading css/js/html etc
Negative scenario testing | include all possible negative scenarios
15 very good tools |  |  | https://www.javacodegeeks.com/2014/12/15-tools-java-developers-should-use-after-a-major-release.html?utm_content=buffer22279&utm_medium=social&utm_source=twitter.com&utm_campaign=buffer

## DiscussWithMayank
Garbage Collection | jvm tuning | performance benchmarking
Memory Optimization
Security | Authorization: Basic xyz | Authentication: Basic | Spring Security | RESTClient
| UserName / Password |  |  | Http Authentication
| MD5 |  |  | Basic Authentication
| Digest |  |  | OAuth Protocol
OAuth
OAuth2
Design Pattern
Caching | ConcurrentHashMap
message resource management
apache camel
Enterprize Architect Questions | http://www.quizover.com/flashcards/what-does-cohesion-mean
N-Tier Architecture
How to secure RESTFul service | use https
performance slow:
1. IO = db / file
2. cpu utilization full / RAM is insufficient
3. IO = blocks
4. Object lock => wait. Soln=> Thread Dump => tool=> thread analyzer=> vlocks thread=> Thread identified
5. Memory Leaks=> OutOfMemory=> heap dump => tools=> MAT tool with Eclipse
6. How GC works
ThreadLocal | Concepts of ThreadLocal in SpringSecurity

## Tech2Learn
Technology | Topics
Design Patterns
Soap Web Service
REST Web Service
Security in Java (Basic, OAuth.....) | Basic, Digest, OAuth, OAuth2
UML Terminology
CoreJava 5,7 Features
| Concurrency & Thread | Executor Framework
Generics
CoreJava 8 Features
Lambda Expression
CoreJava 9 Features
Java EE 5,6,7 Features
AngularJS
Session Management |  | [BEST] https://www.javacodegeeks.com/2018/02/session-management-using-spring-session-jdbc-datastore.html
Micro Profile | Micro Profile | https://start.microprofile.io/
Microservices Related Tech | Zoo Keeper
Ribbon Load Balancer
Eureka - Naming Server
…
…
…

## IQ
We need to build a system that once an order is received will assign the delivery boy and sends notification at every stage of the order such as order received with expected time of delivery, delivery boy assigned, order picked up, order delivered. Design a system that can be horizontally scalable from 100 order to 100 million orders and can perform at almost the same level irrespective of the number of orders received. State how your design will help scale and what will be the performance SLAs that will you will set for your design.
Write the skeleton for an OrderingWebService implementation using Spring MVC. Note that Ordering may include querying, creating, modifying and cancelling orders.
1. How to implement a REST service:: 1) login service 2) get list of objects
security? session_id/cookies should not be stolen.... https. how to configure https?
how to migrate from SOAP to REST
2. Error handling in SOAP web service?
3. Error handling in REST web service?
4